## Source Data
<Company Name>
Project Time Performance Tracking
Project Name | Project Type | Estimated Start | Estimated Finish | Estimated Days | Actual Start | Actual Finish | Actual Days | Variance (in Days) | Estimated Hours | Actual Hours | Variance (in Hours)
Cyberdyne Systems | Terminator Development | 2004-01-04 | 2038-03-04 | 12300 | 2004-01-04 | 2038-04-10 | 12336 | 36 | 200 | 220 | 20
Weyland-Yutani | Alien Invasion | 2004-01-20 | 2004-02-21 | 31 | 2004-01-25 | 2004-02-20 | 25 | -6 | 400 | 390 | -10
Lexcorp | Cloning Superman | 1998-04-10 | 2012-03-10 | 5010 | 1998-04-10 | 2012-03-10 | 5010 | 0 | 500 | 500 | 0
Blue Suns | Mercenary Black Ops | 2012-03-01 | 2012-03-10 | 9 | 2012-03-01 | 2012-06-06 | 95 | 86 | 150 | 145 | -5
Cobra Industries | Battling GI Joe | 2012-01-01 | 2012-01-21 | 20 | 2012-01-01 | 2012-01-21 | 20 | 0 | 250 | 255 | 5
Cerberus | The Lazarus Project | 2083-12-10 | 2086-05-10 | 870 | 2083-10-10 | 2087-10-10 | 1440 | 570 | 300 | 310 | 10
Parallax Corporation | Cost Reduction | 2023-03-10 | 2023-03-20 | 10 | 2023-03-10 | 2023-03-20 | 10 | 0 | 500 | 510 | 10
Tyrell Corporation | Replicant Development | 2004-04-18 | 2004-05-12 | 24 | 2004-04-17 | 2008-03-19 | 1412 | 1388 | 750 | 790 | 40
Virtucon | Fembot Refactoring | 2004-05-12 | 2004-06-22 | 40 | 2004-05-15 | 2004-06-24 | 39 | -1 | 450 | 430 | -20
Omni Consumer Products | ED-209 Bugfixes | 2012-03-10 | 2013-03-10 | 360 | 2012-08-19 | 2018-08-19 | 2160 | 1800 | 230 | 235 | 5
TOTAL |  |  |  | 18674 |  |  | 22547 | 3873 | 3730 | 3785 | 55